## Effort tracking
Month | Planned | Actual | Short Month | Month Number
January | 0 | 0 | Jan | 1
February | 10000 | 24000 | Feb | 2
March | 15000 | 27000 | Mar | 3
April | 20000 | 40000 | Apr | 4
May | 40000 | 50000 | May | 5
June | 45000 | 73000 | Jun | 6
July | 70000 | 50000 | Jul | 7
August | 75000 | null | Aug | 8
September | 80000 | null | Sep | 9
October | 85000 | null | Oct | 10
November | 92000 | null | Nov | 11
December | 99800 | null | Dec | 12

## Budget Forecast
Month | Budget | Actuals | Forecast | Short Month | Index
January | 50000 | 49000 | 49000 | Jan | 1
February | 80000 | 76000 | 60000 | Feb | 2
March | 80000 | 78000 | 73000 | Mar | 3
April | 75000 | 81000 | 75000 | Apr | 4
May | 90000 | 99000 | 84000 | May | 5
June | 100000 | 95000 | 90000 | Jun | 6
July | 100000 | 85000 | 90000 | Jul | 7
August | 90000 | null | 92000 | Aug | 8
September | 93000 | null | 94000 | Sep | 9
October | 85000 | null | 97000 | Oct | 10
November | 99000 | null | 99000 | Nov | 11
December | 95000 | null | 100000 | Dec | 12

## Tasks
Milestone1 | Installation1 | In Progress | 25 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute
Milestone1 | Installation II | In Progress | 75 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute, Andy Bernard
Milestone1 | Wiring I | Not started | 10 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute, Andy Bernard
Milestone1 | Wiring II | Not started | 15 | 7/30/21 | Dwight Schrute, Andy Bernard
Milestone1 | Demo | Not started | 60 | 7/30/21 | Micheal Scott, Jim Halpert
Milestone1 | Milestone2 | In Progress | 50 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute, Andy Bernard
Milestone2 | Installation II | In Progress | 80 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute, Andy Bernard
Milestone2 | Wiring I | In Progress | 100 | 7/30/21 | Micheal Scott, Jim Halpert
Milestone2 | Wiring II | In Progress | 10 | 7/30/21 | Dwight Schrute, Andy Bernard
Milestone2 | Demo | In Progress | 33 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute
Milestone2 | Research | In Progress | 75 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute, Andy Bernard
Milestone2 | Telemetry | In Progress | 95 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute, Andy Bernard
| Task1 | In Progress | 89 | 7/30/21 | Micheal Scott, Jim Halpert, Dwight Schrute, Andy Bernard
| Task2 | Completed | 100 | 7/30/21 | Micheal Scott

## Resources
Name | Image URL
Jon Harrington | https://images.unsplash.com/photo-1582233479366-6d38bc390a08
Resource1 | https://images.unsplash.com/photo-1507003211169-0a1dd7228f2d
Resource2 | https://images.unsplash.com/photo-1597223557154-721c1cecc4b0
Resource3 | https://images.unsplash.com/photo-1546456073-92b9f0a8d413
Resource4 | https://images.unsplash.com/photo-1552374196-c4e7ffc6e126

## Horizontal
Late Tasks | Not started tasks | Pending expense approvals | Pending time approvals | Overbooked resources | Overdue resource requests
4 | 12 | 4 | 12 | 2 | 1

## Project Manager
Manager | Image URL
Jon Harrington | https://images.unsplash.com/photo-1582233479366-6d38bc390a08

## Project Details
Project Id | 100029
Customer | USPM
Estimated Start Date | 2021-01-01
Estimated End Date | 12-31-2021
Estimated Total Cost | $2000000

## Vertical
Remaining Effort | Booking Shortage (this week) | Schedule variance | Cost variance
100 | -10 | -24 | -60000